## Sheet1
| Task Name | Description | Deliverables/ Checkpoints | Duration (Hours) | People | Predecessors
1 | Understand Client Requirements | Develop a clear understanding of the client's expectations and what the project is meant to achieve. | Initial Project Statement | 2 | Joshua
|  |  | Data Collection | 2 | Tim
|  |  | Consumer Needs | 2 | Brian
|  |  | Research Prior Design | 2 | Dylan
|  |  | Objective Tree | 2 | Jordan
|  |  | Pairwise Charts | 2 | Austin
|  |  | Problem Definition | 2 | Joshua
2 | Examine Functional Necessities | Determine what the project is meant to do and begin considering ways to do it. | Brainstorm on Functions | 3 | All
|  |  | Develop Initial Requirements | 2 | Tim
|  |  | Eliminate Extraneous Ideas | 1.5 | All
3 | Concept Development | Develop the ideas on how to acomplish our goals and implement relevant technology and ideas. | Generate Ideas | 2 | All | 1,2
|  |  | Brainstorm | 2 | All
|  |  | List All Alternates | 2 | All
|  |  | Evaluate Possibilities | 2 | Dylan
|  |  | Eliminate Extraneous Ideas | 1 | Brian
4 | Preliminary Design | Develop a preliminary design to move toward creating the device and better eliminate future problems | Compare Concepts | 2 | All | 3
|  |  | Evaluate Objective Achievement | 1 | Austin/Joshua
|  |  | AutoCad Drafts | 5 | Joshua/Austin
|  |  | Review With Client | 1 | Jordan
|  |  | Eliminate Extraneous Ideas | 1 | All
5 | Detailed Design | Finalize the design and dimensions of the project | Final AutoCad Draft | 5 | Tim/Brian | 4
6 | Circuit Development | Design and implement the circuitry required for the device. | Circuitry Design | 5 | Austin/Tim | 3,4,5
|  |  | Verification | 3 | Austin/Tim/Joshua
|  |  | Purchase Components | 2 | Brian
|  |  | Circuit Creation | 3 | Dylan/Jordan
|  |  | Circuit Testing | 3 | Dylan/Jordan
7 | Software Development | Design and test the software required to interface with the hardware | Input/output recognition | 3 | Tim/Joshua | 3,4,5
|  |  | Code Generation | 3 | Joshua/Jordan
|  |  | Code Testing | 3 | Joshua/Jordan
|  |  | Code Implementation | 3 | Tim/Austin
8 | Hardware Development | Design and create the hardware required | Hardware Design | 5 | Austin/Brian | 3,4,5
|  |  | Verification | 3 | 3,4
|  |  | Purchase Components | 2 | Brian
|  |  | Hardware Creation | 2 | Brian/Austin
|  |  | Hardware Testing | 3 | Brian/Austin
9 | Document Design Process | Develop the final documents detailing every aspect of the project | Draft Final Report | 5 | Jordan/Dylan | 6,7,8
|  |  | Review With Client | 1 | Jordan
10 | Compilation | Compile all portions of the project to create the working model | Circuit/Code Combination | 2 | Brian/Austin | 7,8,9
|  |  | Total Combination | 5 | All
|  |  | Fix Issues | 5 | All
6 | Document Design Process | Develop the final documents detailing every aspect of the project | Draft Final Report | 5 | Jordan/Dylan | 5,7,8
|  |  | Review With Client | 1 | Jordan
7 | Circuit Development | Design and implement the circuitry required for the device. | Circuitry Design | 5 | Austin/Tim | 3,4,5
|  |  | Verification | 3 | Austin/Tim/Joshua
|  |  | Purchase Components | 2 | Brian
|  |  | Circuit Creation | 3 | Dylan/Jordan
|  |  | Circuit Testing | 3 | Dylan/Jordan
8 | Software Development | Design and test the software required to interface with the hardware | Input/output recognition | 3 | Tim/Joshua | 3,4,5
|  |  | Code Generation | 3 | Joshua/Jordan
|  |  | Code Testing | 3 | Joshua/Jordan
|  |  | Code Implementation | 3 | Tim/Austin
9 | Hardware Development | Design and create the hardware required | Hardware Design | 5 | Austin/Brian | 3,4,5
|  |  | Verification | 3 | 3,4
|  |  | Purchase Components | 2 | Brian
|  |  | Hardware Creation | 2 | Brian/Austin
|  |  | Hardware Testing | 3 | Brian/Austin
10 | Compilation | Compile all portions of the project to create the working model | Circuit/Code Combination | 2 | Brian/Austin | 7,8,9
|  |  | Total Combination | 5 | All
|  |  | Fix Issues | 5 | All