## Sheet1
| Task Name | Description | Deliverables/ Checkpoints | Duration (Hours) | People | Predecessors
1 | Project Management
1.1 | Understand Client Requirements | Develop a clear understanding of the client's expectations and what the project is meant to achieve. | Deliverable 1 | 2 | Joshua
1.2 | Data Collection | Collect data to find out what the project requires |  | 2 | Tim
1.3 | Consumer Needs | Determine the needs of the consumer so that the project achieves exactly what he or she wants it to |  | 2 | Brian
1.4 | Research Prior Design | Research past technology to avoid repeating their work and mistakes |  | 2 | Dylan
1.5 | Objective Tree | Describes the objectives of the projects and details of those objectives |  | 2 | Jordan
1.6 | Pairwise Charts | Determines the Weight that each objective is assigned and why |  | 2 | Austin
1.7 | Problem Definition | Uses the research and charts to re-evaluate the problem statement |  | 2 | Joshua
2 | Engineering requirements |  | Deliverable 2
2.1 | Examine Functional Necessities | Determine what the project is meant to do and begin considering ways to do it. |  | 3 | All | 1
2.2 | Develop Initial Requirements | Determine what is required in the beginning to understand the parameters our device will operate under |  | 2 | Tim
2.3 | Eliminate Extraneous Ideas | "think free" and then eliminate the ideas that obviously will not work e.g elephants controlling dishwashers |  | 1.5 | All
3 | Concept Development | Develop the ideas on how to acomplish our goals and implement relevant technology and ideas. | Deliverable 3 | 2 | All | 1,2
3.1 | Brainstorm | Come up with free ideas that we might be able to use or combine to make one good idea | Deliverable 4 | 2 | All
3.2 | List All Alternates | list brainstormed ideas and determine a variety of ideas that can be used |  | 2 | All
3.3 | Evaluate Possibilities | Evaluate the ideas we came up with and the techniques we can use to make our project better. Objectively rank them to give a better understanding of which is the best to use |  | 2 | Dylan
3.4 | Eliminate Extraneous Ideas | "think free" and then eliminate the ideas that obviously will not work e.g elephants controlling dishwashers |  | 1 | Brian
4 | Circuit Development | Design and implement the circuitry required for the device. | Circuitry Design/simulator | 5 | Austin/Tim | 3
4.1 | Verification | Verify that the circuit works | simulation | 3 | Austin/Tim/Joshua
4.2 | Purchase Components | Buy components of the circuit for testing and implementation | Review with Client | 2 | Brian
4.3 | Circuit Creation | build circuit to prepare for implementation |  | 3 | Dylan/Jordan
4.4 | Circuit Testing | implement the circuit and test it |  | 3 | Dylan/Jordan
5 | Software Development | Design and test the software required to interface with the hardware | Input/output recognition | 3 | Tim/Joshua | 3
5.1 | Code Generation | Generate code to interface with the circuit |  | 3 | Joshua/Jordan
5.2 | Code Testing | test the code to make sure it works |  | 3 | Joshua/Jordan
5.3 | Code Implementation | implement the code in the circuit by loading it on the microcontroller |  | 3 | Tim/Austin
6 | Mechanical Development | Design and create the hardware required | AutoCad Design | 5 | Austin/Brian | 3
6.1 | Verification | Verify the mechanical design is sound |  | 3 | All
6.2 | Purchase Components | buy the components and ensure that the parts fit together | Review with client | 2 | Brian
6.3 | Hardware Creation | Begin construction of the device |  | 2 | Brian/Austin
6.4 | Hardware Testing | Test the device and ensure it does all that is required | Final AutoCad Design | 3 | Brian/Austin
7 | Compilation | Compile all portions of the project to create the working model | Draft Final Report | 2 | All | 4,5,6